## Sheet1
Health Care APP WBS
[11 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11
ID | Phase | Activity Name | Description | Responsibilities | Procedure | Start Week | End Week | Duration | Start Date | EndDate | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17
Phase 1: Project Initiation
1.1 | Intiation | Project idea Selection | Define Problem , target user & benift | Project Manager | - | Week 1 | Week 1 | 1 | 2026-06-02 | 2026-06-02 | X
1.2 | Intiation | Project proposal Preparation | Write Propsal With Objective, socpe & feasibilty | All Members | 1.1 | Week 1 | Week 1 | 1 | 2026-06-02 | 2026-06-02 | X
1.3 | Intiation | Project CharterDevelopment | Prepare charter with milestone & stakeholders | Project Manager | 1.2 | Week 1 | Week 1 | 1 | 2026-06-02 | 2026-06-02 | X
Phase 2: Requiremnet and Planning
2.1 | Planning | Reuirement Gathering | Collect Functional & non-funational Requirments | Business Analyst | 1.3 | Week 1 | Week 1 | 7 | 2026-06-02 | 2026-06-08 | X | X | X | X | X | X | X
2.2 | Planning | System analysis & Risk identification | Analyze requirement,define architecture & idetification | Team lead | 2.1 | Week 2 | Week 2 | 7 | 2026-06-09 | 2026-06-15 | [7 empty] | X | X | X | X | X | X | X
2.3 | Planning | Budget & Resource Planning | Finalize budget & assigne team role | Project Manager | 2.2 | Week 2 | Week 2 | 7 | 2026-06-09 | 2026-06-15 | [7 empty] | X | X | X | X | X | X | X
Phase3: System Design
3.1 | Design | UI/Ux Design | Design screen for Patients,doctors & pharmcistsis | UI/UX Designer | 2.3 | Week 3 | Week 3 | 7 | 2026-06-16 | 2026-06-22 | [14 empty] | X | X | X | X | X | X | X
3.2 | Design | Database & Archtecture Design | Design Firebase DB schema & Ract-native architecture | Backend developer / Tech lead | 3.1 | Week 3 | Week 3 | 7 | 2026-06-16 | 2026-06-22 | [14 empty] | X | X | X | X | X | X | X
Phase4: Development
4.1 | Development | Patient Registration & Login | Develop secure Login & registration system | Frontend developer | 3.2 | Week 4 | Week 4 | 7 | 2026-06-23 | 2026-06-29 | [21 empty] | X | X | X | X | X | X | X
4.2 | Development | Online Doctor Consultation Module | Build appointmnet booking & video consultation | Full Stack developer | 4.1 | Week 4 | Week 5 | 14 | 2026-06-23 | 2026-07-06 | [21 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X
4.3 | Development | Medicine Ordering & Delivery | Prescription upload ,order & tracking system | Full Stack developer | 4.2 | Week 5 | Week 6 | 14 | 2026-06-30 | 2026-07-13 | [28 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X
4.4 | Development | Lab Test Booking & Report | Labbooking,sample Collection & report module | Backend developer | 4.3 | Week 6 | Week 7 | 14 | 2026-07-07 | 2026-07-20 | [35 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X
4.5 | Development | Payment & Notification System | Integrate EasyPaisa/JazzCash & push notification | Backend developer | 4.4 | Week 7 | Week 7 | 7 | 2026-07-14 | 2026-07-20 | [42 empty] | X | X | X | X | X | X | X
4.6 | Development | Admin Dashboard | Build admin panel for user mangemnt&monitor | Full Stack developer | 4.5 | Week 7 | Week 8 | 14 | 2026-07-14 | 2026-07-27 | [42 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Phase5: Testing and QA
5.1 | Testing | Unit & Integration testing | Testing indiviual modules & their integrataions | QA Engineer | 4.6 | Week 9 | Week 9 | 7 | 2026-07-28 | 2026-08-03 | [56 empty] | X | X | X | X | X | X | X
5.2 | Testing | User Acceptance & Security Testing | UAT with real users & performance/security check | QA + Project Manager | 5.1 | Week 9 | Week 9 | 7 | 2026-07-28 | 2026-08-03 | [56 empty] | X | X | X | X | X | X | X
Phase6: Deployment
6.1 | Deploymnet | Cloud steup & App store Deployment | configure Firebase server & deploy to google | DevOps / Developer | 5.2 | Week 10 | Week 10 | 7 | 2026-08-04 | 2026-08-10 | [63 empty] | X | X | X | X | X | X | X
6.2 | Deploymnet | User Traning | Train doctors, Pharmacists & Lab Technicians | Project Manager | 6.1 | Week 10 | Week 10 | 7 | 2026-08-04 | 2026-08-10 | [63 empty] | X | X | X | X | X | X | X
Phase7: Project CLosure
7.1 | Closure | Documentation Submission | Finalize & submit all project documnetation | All Members | 6.2 | Week 11 | Week 11 | 7 | 2026-08-11 | 2026-08-17 | [70 empty] | X | X | X | X | X | X | X
7.2 | Closure | Final Project review & Sign-off | conduct final review meeting & get sign-off | Project Manager | 7.1 | Week 11 | Week 11 | 7 | 2026-08-11 | 2026-08-17 | [70 empty] | X | X | X | X | X | X | X