## Resource List
Resource Sheet |  |  |  |  | Resource Assigned
Resource Name | Type | Std Rate | Role | Max unit | Task /Resource Name | Assigned Resource
Project Manager | work | 1000/hr | Managemnet | 75% | Project Idea Selection | Project Manager
Business Analyst | work | 800/hr | Planning | 100% | Project Proposal Preparation | Project Manager
UI/UX Designer | work | 700/hr | Design | 100% | Project Charter Development | Project Manager
Frontend Developer | work | 900/hr | Development | 100% | Requirement Gathering | Business Analyst
Backend Developer | work | 900/hr | Development | 100% | System Analysis & Risk Identification | Business Analyst
QA Engineer | work | 600/hr | Testing | 100% | Budget & Resource Planning | Project Manager
DevOps Engineer | work | 850/hr | Deploymnet | 70% | UI/UX Design | Ui/UX Designer
[5 empty] | Database & Architecture Design | Ui/UX Designer, Backend Developer
[5 empty] | Patient Registration & Login Module | Backend Developer , DevOps, Frontendend Developer
[5 empty] | Online Doctor Consultation Module | Backend Developer , DevOps, Frontendend Developer
[5 empty] | Medicine Ordering & Delivery Module | Backend Developer , DevOps, Frontendend Developer
Working Hours |  |  |  |  | Lab Test Booking & Report Module | Backend Developer , Frontendend Developer
[5 empty] | Payment & Notification System | Backend Developer , Frontendend Developer
Resource | Est Date | Working Hrs |  |  | Admin Dashboard Development | Backend Developer , Frontendend Developer
Project Manager | 31 | 248 |  |  | Unit & Integration Testing | QA Enginer
Business Analyst | 14 | 112 |  |  | User Acceptance Testing | QA Enginer
UI/UX Designer | 7 | 56 |  |  | Cloud Setup & App Deployment | DevOps Enginer
Frontend Developer | 70 | 560 |  |  | User Training | Project Manager
Backend Developer | 77 | 616 |  |  | Documentation Submission | Project Manager
QA Engineer | 14 | 112 |  |  | Final Project Review & Sign-off | Project Manager
DevOps Engineer | 21 | 168
Total Working hours |  | 1872
OverAllocation Resources
overallocated Resource | Problem Task | Overallocteed Detail | Solution applied | Status
Project Manager | No Overallocataion | Resource demand 75% exceeded | Resource Level (Level All) | Resolved
DevOps Engineer | 4.1,4.2,4.3,6.1 | Assigned beyond 70% max unit | Resource Level (Level All) | Resolved
| Issue | Sol
| Resource overallocation detected | Resolved using Resource Leveing

## Resource Assigned
Resource Assigned
Task /Resource Name | Assigned Resource
Project Idea Selection | Project Manager
Project Proposal Preparation | Project Manager
Project Charter Development | Project Manager
Requirement Gathering | Business Analyst
System Analysis & Risk Identification | Business Analyst
Budget & Resource Planning | Project Manager
UI/UX Design | Ui/UX Designer
Database & Architecture Design | Ui/UX Designer, Backend Developer
Patient Registration & Login Module | Backend Developer , DevOps, Frontendend Developer
Online Doctor Consultation Module | Backend Developer , DevOps, Frontendend Developer
Medicine Ordering & Delivery Module | Backend Developer , DevOps, Frontendend Developer
Lab Test Booking & Report Module | Backend Developer , Frontendend Developer
Payment & Notification System | Backend Developer , Frontendend Developer
Admin Dashboard Development | Backend Developer , Frontendend Developer
Unit & Integration Testing | QA Enginer
User Acceptance Testing | QA Enginer
Cloud Setup & App Deployment | DevOps Enginer
User Training | Project Manager
Documentation Submission | Project Manager
Final Project Review & Sign-off | Project Manager

## Working Hours
Working Hours
Resource | Est Date | Working Hrs
Project Manager | 31 | 248
Business Analyst | 14 | 112
UI/UX Designer | 7 | 56
Frontend Developer | 70 | 560
Backend Developer | 77 | 616
QA Engineer | 14 | 112
DevOps Engineer | 21 | 168
Total Working hours |  | 1872