## Budget Estimation
Resource Cost Estimation
Resource Name | Role | Std. Rate ($/hr) | Total Working Hours | Total Cost ($)
Project Manager | Project Management | 1000 | 200 | 200000 |  |  | Resource Chart
Business Analyst | Requirement Analysis | 800 | 112 | 89600
UI/UX Designer | UI/UX Design | 700 | 112 | 78400
Frontend Developer | Frontend Development | 900 | 647.36 | 582624
Backend Developer | Backend Development | 900 | 703.36 | 633024
QA Engineer | Testing & QA | 600 | 112 | 67200
DevOps Engineer | Deployment & Cloud | 850 | 423.36 | 359856
Grand Total |  |  |  | 2010704
Task Cost Estimation
Task ID | Task Name | Resource | Duration (Days) | Working Hours | Rate/Hour ($) | Total Cost ($)
1.1 | Project Idea Selection | Project Manager | 1 | 8 | 1000 | 8000
1.2 | Project Proposal Preparation | Project Manager | 1 | 8 | 1000 | 8000
1.3 | Project Charter Development | Project Manager | 1 | 8 | 1000 | 8000
2.1 | Requirement Gathering | Business Analyst | 7 | 56 | 800 | 44800
2.2 | System Analysis & Risk Identification | Business Analyst | 7 | 56 | 800 | 44800
2.3 | Budget & Resource Planning | Project Manager | 7 | 56 | 1000 | 56000
3.1 | UI/UX Design | UI/UX Designer | 7 | 56 | 700 | 39200
3.2 | Database & Architecture Design | UI/UX Designer + Backend Developer | 7 | 56 | 1600 | 89600 | Task Budget Chart:
4.1 | Patient Registration & Login Module | Backend + DevOps + Frontend | 9.1 | 72.8 | 2650 | 192920
4.2 | Online Doctor Consultation Module | Backend + DevOps + Frontend | 18.41 | 147.28 | 2650 | 390292
4.3 | Medicine Ordering & Delivery Module | Backend + DevOps + Frontend | 18.41 | 147.28 | 2650 | 390292
4.4 | Lab Test Booking & Report Module | Backend + Frontend | 14 | 112 | 1800 | 201600
4.5 | Payment & Notification System | Backend + Frontend | 7 | 56 | 1800 | 100800
4.6 | Admin Dashboard Development | Backend + Frontend | 14 | 112 | 1800 | 201600
5.1 | Unit & Integration Testing | QA Engineer | 7 | 56 | 600 | 33600
5.2 | User Acceptance Testing | QA Engineer | 7 | 56 | 600 | 33600
6.1 | Cloud Setup & App Deployment | DevOps Engineer | 7 | 56 | 850 | 47600
6.2 | User Training | Project Manager | 7 | 56 | 1000 | 56000
7.1 | Documentation Submission | Project Manager | 7 | 56 | 1000 | 56000
7.2 | Final Project Review & Sign-off | Project Manager | 7 | 56 | 1000 | 56000
Grand Total | [5 empty] | 2058704
Total Project Budget
Resource Cost Estimation - Grand Total | [5 empty] | 2010704
Task Cost Estimation - Grand Total | [5 empty] | 2058704
TOTAL PROJECT BUDGET | [5 empty] | 4069408